# TERMS OF REFERENCE

# Mid-term review - gIVING FOR cHANGE Project

| Project | Giving for Change Project |
| --- | --- |
| Consultancy duration | June – July 2023 |
| Position Title | Research Consultant |
| Reporting to | Results and Learning Manager, STAR Ghana Foundation |

## 1.0 Introduction to STAR-Ghana Foundation

The STAR-Ghana Foundation is a national centre for active citizenship and philanthropy. The vision of STAR Ghana Foundation is a well-informed civil society able to contribute to transformational change around key challenges of poverty, inequality, and inclusion for all citizens. The mission of STAR Ghana Foundation is to increase the effectiveness of citizen influence for change that advances democracy, accountability, and social inclusion. The Foundation achieves its mission through the roles of a Convener, Catalyst and Coordinator of civil society action towards systemic and transformational change in Ghana. It builds on the results and lessons of the STAR-Ghana programme, a 10-year civil society support initiative funded by DFID, DANIDA and the European Union.

2.0 Background - Giving for change project

Giving for Change (GfC) is a five-year programme which sets out a bold vision for transforming how “development is done” by focusing specifically on the recognition and importance of domestic resources in increasing local ownership, unlocking agency and strengthening communities’ ability to express and claim their rights from other stakeholders, including governments and international development institutions. The programme aims to advance the theory and practice of community philanthropy as a development strategy. Community philanthropy, which itself is an emergent body of work, is based on the premise that all communities have their own assets (money, skills, knowledge, networks, etc.) and that when these are pooled together, they build community power and voice and enable people to become co-investors in their own development. By drawing learning from current theory and practice, supporting and piloting new and emerging models of community philanthropy, and contributing to enabling environment, Giving for Change seeks to foster the conditions in which public participation, collective action and the expression of rights can thrive. The issue of power is central to programme: in addition to an explicit focus on strengthening communities’ abilities to claim rights and entitlements from public government structures, Giving for Change also seeks to overcome power dynamics and establish more equitable practices within the international development system itself.

Giving for Change is funded under the Dutch Ministry of Foreign Affairs’ strengthening civil society policy framework. The components of the programme are structured around three domains.

- Central domain: to unlock the collective power of local communities, represented by Civil Society Actors, to express their opinion through community philanthropy.

- Domain 2: Influence in-country national state and societal actors to support community philanthropy and domestic philanthropic giving.

- Domain 3: Challenge and change the existing practices of international development donors.

The Giving for Change alliance comprises anchor partners from eight countries, and four consortium partners working at the international level, each of which shares the vision of community-led development through community and domestic philanthropy.

In Ghana, STAR Ghana Foundation is the Anchor Institution for Ghana, with WACSI as a Strategic Partner.

The project has a dual focus to promote;

- Civic and civil society space and strengthen communities’ ability to claim rights and entitlements from different actors, particularly government.

- Domestic resources, through philanthropy, including local giving for transformational social change.

To date, the project has engaged a total of 34 civil society organisation organisations. These organisations belong to one of the three COPs formed. Additionally, the project provided seed funding to 5 organisations and a match funding to 7 CSOs to undertake various initiatives that promotes local philanthropy and fosters an enabling environment for resource mobilization to thrive.

3.0 Purpose of the Review

At the mid-point of project implementation, the Giving for Change alliance is seeking to undertake a review to determine progress made so far under the programme and the extent to which it is on track to deliver against its objectives.

The purpose of the Mid-term review (MTR) is to reflect on progress and learnings so far, both at the community and the national level, and help identify potential changes or adjustments that will help enhance the programme and increase the likelihood of its success. Information will be gathered to enable programme – both at individual organisations and collective to answer a number of key questions regarding progress that have been made so far and areas for further development and reflections. Findings from the MTR will help frame priorities, plans and activities for the remaining period of the programme and beyond.

In view of this, the programme seeks a consultant who would work closely with the international consultant to harvest results and outcomes at the community and national level and also contribute to a larger, programme-wide learning.

## 4.0 Scope of the Work Required

Generally, the task of the consultant will be to engage partners implementing under the project, including community based and national-level actors. The local consultant will further engage the international consultant to ensure that the activities and focus of the review meet the specific national and contextual requirements and that can be aggregated, synthesized and considered collectively at the global level.

Specifically, the work will require developing the methodology and tools with the international consultant, undertaking the study (data collection and analysis) and producing an independent report that will inform the project about the overall progress of work (including documented diverse models of local philanthropy), while ensuring that the process of the review strengthens the project and its partners in delivering on their priorities.

Task 1: Prepare Inception report

The consultant will prepare and present an inception report to demonstrate understanding of the assignment, the methodology to use, and a detailed work plan. The proposed methodology will be approved by SGF prior to implementation of the remaining tasks in this TOR. The methodology will spell out among other things:

- The consultant’s understanding of the assignment.

- The conceptual framework for the study;

- Description of methodology for the study;

Task 2: Undertake the study + draft a report on preliminary compilations and findings

The Consultant will undertake the study in accordance with the agreed methodology and prepare a draft report which draws out progress of implementation and learning during the period under study. The draft report will be submitted to the SGF for review.

Task 3: Validation of findings with SGF and Partners

The report will further be validated by a larger group (SGF and some selected partners) to ensure a fair representation of progress made.

Task 4: Produce and Submit a finalised report

The report will be revised based on the feedback from the initial reviews and validation.

## 5.0 Deliverables

## The Consultant will provide the following deliverables:

- An inception report with the detailed work plan and a detailed methodology

- Final tools/instruments of the study

- Draft study report

- Presentation of the key findings to the SGF and Partners for validation

- Final Mid-term review report

6.0 Level of Efforts

A total of 12 days is allocated for this task, and split as follows;

| Activity | Estimated number of days | Timeline |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | June (4th Wk) | July (1st – 3rd Week) |  |  |
|  |  | Wk1 | Wk2 | Wk3 | Wk4 |
| Inception meeting with SGF and WACSI | 1 |  |  |  |  |
| Desk review and Field work | 7 |  |  |  |  |
| Report preparation | 2 |  |  |  |  |
| Presentation of report for validation | 1 |  |  |  |  |
| Finalization of report | 1 |  |  |  |  |

7.0 Key Relationships

Heads of Programmes: Will provide overall strategic input for implementation of the assignment.

Results and Learning Manager: Will provide overall coordination of the implementation of the assignment.

Project Officer: Will ensure and manage the day-to-day implementation of the assignment including arranging inputs from other staff and stakeholders as required and access to relevant documents.

8.0 Competencies

The consultant must demonstrate the following skills and competencies;

- Strong analytical skills in designing and conducting surveys

- Ability to communicate excellently and to produce high quality research reports

- Evidence of experience with similar assignments

- Ability to work collaboratively with all stakeholders, demonstrating capacity to work with feedback