# Terms of Reference: Mapping of Peace and Security Initiatives and Actors in Northern Ghana

As a result of the current security situation and the growing threats (both internal and external) of insecurity especially in northern Ghana, the landscape is replete with initiatives and actions being implemented by both state and non-state actors. Currently there is no database of what is ongoing and by whom, making it difficult for actors to effectively coordinate among themselves. Therefore, STAR-Ghana Foundation is seeking to recruit a consultant to undertake a mapping exercise on peace and security initiatives and actions being implemented across the five (5) regions of northern Ghana to support the Regional Coordinating Councils and other actors to coordinate effectively.

Closing Date: 13th December 2023 
Type:  Individual Consultant 
Duration: December 2023 to February 2024

Scope of work:

This assignment entails mapping all ongoing and potential actions (including projects, programmes, initiatives, processes etc) on peace and security by various actors – both state and non-state, in northern Ghana. It is intended to create a database of ongoing and existing initiatives in peace and security in Northern Ghana to get a better sense of the landscape for effective coordination. The assignment will therefore involve mapping of initiatives and actions currently being implemented across the five (5) regions of northern Ghana by state and non-state actors. For each initiative/action, the mapping will cover its objectives; key actors/stakeholders involved; geographic coverage; period of implementation; funder(s); and key contact person(s).

## Background

## Northern Ghana has a history of inter- and intra-ethnic conflicts which have negatively affected the development of the area, considered to be the poorest and most underdeveloped art of Ghana. In addition to these, the high rates of unemployment and poverty, coupled with growing threats of violent extremism and terrorism have altered the dynamics of insecurity in northern in northern Ghana even more, with implications for not just the development and stability of the north alone, but that of the entire country.

## In response, a number of actions in the form of projects, programmes, campaigns amongst others led by various actors have been put in place over the years. More recently, the Government, through the Ministry of National Security, has developed and launched the National Security Strategy (NSS) to provide an overarching framework for the nation’s response to insecurity and the threat of violent extremism. Out of this, the National Framework for Preventing and Countering Violent Extremism and Terrorism (NFPCVET) as well as the National Border Security (NSS) were developed as action plans for preventing and countering insecurity, radicalization, and violent extremism. At the regional and district levels, the Regional Security Councils (REGSECs) and District Security Councils (DISECs) are implementing actions aimed at strengthening the nation’s capacity to respond to existing and potential threats to peace and security.

## Complementing the efforts of the state, civil society organisations and development partners have equally been implementing various actions across northern Ghana to contribute to addressing specific conflicts, but also targeted at addressing the drivers of violence and insecurity and building resilience against vulnerability to radicalization and violent extremism.

## While collaboration and coordination between actions of state and non-state actors (and within state and nonstate actors) has been relatively good, it lacks structure, hence is often adhoc, uncoordinated and sometimes counterproductive. The Regional Coordinating Councils (RCCs) that are mandated by law to play the lead coordination role are not given the needed support to do so effectively. Given the enormity of the challenges and the risk of duplication in the face of dwindling funding, the implications of failure are dire. A re-examination of the ways of working to enhance the effectiveness of the actions of actors is therefore required.

## The Dialogue of State and Non-state Actors

## Against this background, STAR-Ghana Foundation (SGF) in collaboration with the five Regional Coordinating Councils (RCCs) of northern Ghana in March 2023 in Tamale in the northern region organized the first dialogue of state and nonstate actors for security coordination in northern Ghana, to discuss and agree on an effective mechanism for better coordination among actors to achieve efficient outcomes in peace and security in northern Ghana. This dialogue is now institutionalized as a biannual coordination dialogue. The 2nd consecutive dialogue happened in November 2023 at Bolgatanga in the Upper East region.

## In both the first and second dialogues, stakeholders strongly recommended the need for a database of all the peace and security actions and actors working across northern Ghana, as a basis for effective coordination among stakeholders on peace and security. This assignment will respond to this need.

## Approach and scope of work

## A mixed method approach is recommended for this assignment. It will involve desk review of relevant literature. It will also involve primary data gathering through key informant interviews, expert interviews and administering of questionnaire.

## The consultant will develop an appropriate tool/template for the mapping exercise and produce region specific reports cataloguing peace and security actions and actors in each of the five (5) regions of the norther. S/he will also synthesise the five (5) separate reports into a consolidated report on northern Ghana, focusing on overlapping actions and actors that work across regions. It will also make recommendations on effective ways to streamline and coordinate better.

## The final consolidated report is expected to be presented during the 3rd dialogue of state and nonstate actors on security coordination in northern Ghana.

## Activities and deliverables

| ## SN | ## Deliverable | ## Activities |
| --- | --- | --- |
| ## 1 | ## Inception Report detailing plan of work and budget | - Prepare detailed assignment plan. - Propose detailed workplan and field budget. |
| ## 2 | ## Data collection Tools | - Draft tool/template for data collection for review and approval by SGF |
| ## 3 | ## Data Collection and Analysis | - Deploy the tool/template to collect data. - Collate, clean and synthesis data for analysis and reporting |
| ## 4 | ## Draft Interim Reports | - Draft region-specific reports and a consolidated report based on data collected. - Incorporate feedback from SGF into reports. |
| ## 5 | ## Final Reports | - Submit 6 final reports – 5 regional specific reports and a consolidated report. - Participate and present consolidated report at 3rd dialogue of state and nonstate actors on peace and security coordination in northern Ghana. |

## Management and support

- The Executive Director of STAR-Ghana Foundation, supported by the Head of Programmes, will be the main interface between the Consultant and the Foundation. They will provide strategic level support and information necessary for the timely execution of deliverables.

- The Project Manager will provide technical and operational support to the Consultant to facilitate the work.

## Qualifications

The preferred consultant will meet the following minimum specifications:

- Hold at least a master’s degree in a relevant field with a strong background in research.

- Have demonstrable experience and record in undertaking similar assignments.

- Strong understanding of the peace and security context of northern Ghana

- Strong ability to identify and engage key personalities and/or institutions as may be necessary for the successful execution of the assignment.

- Ability and availability to travel to the field for the purposes of data collection and as would be necessary for completing the assignment.

- Have good understanding of conflict and cultural sensitivity around the theme for the assignment.

- Excellent written and communication skills

Please note that this is only the minimum requirement, and that final selection will be based on an assessment of the quality of all EOIs that will be received for this assignment. Therefore, merely meeting the minimum requirements above does not necessarily guarantee selection for the assignment.

## Expression of Interest

## Interested consultant(s) should share a technical proposal that includes the following:

- A short 1/2-page proposal that reflects your own understanding of the assignment.

- Indicative timelines for delivery of the main activities

- Financial proposal for the assignment

- Profile and CV of the consultant(s)

- Overview and evidence of relevant assignments in the last 5 years

- At least 3 references client organizations and key contact persons (include name; email address and mobile number)

## How to apply

The Expression of Interest (EoI) should be submitted via e-mail with the subject line: EOI to Conduct Mapping of Peace & Security Actions in Northern Ghana _APPLICANT’S NAME to: info@star-ghana.org by close of business on Wednesday 13th December 2023.

Questions or requests for clarifications should be directed to: Aatimpe@star-ghana.org CC: EAgbenyadzi@star-ghana.org

## About STAR-Ghana Foundation

STAR Ghana Foundation (SGF) is a registered national civil society organisation which works towards the development of a vibrant, well-informed, and assertive civil society able to contribute to transformational national development and inclusive access to high quality, accountable public services for all Ghanaian citizens. For more information, visit our website on: https://www.star-ghana.org/